## tasks
Task	Duration
Develop AHF2.0	3 weeks
fill in local values/make game balanced	2 weeks
revise proposal	1 week
reach out to schools	1 week
develop curriculum around AHF	2 weeks
Make questionnaire	3 days
conduct research on schools	2-3 weeks
process results	1-2 weeks
write thesis	3 weeks

## Game dev todo
Functional	aesthetical	planning
refactor to use grid in stead of dictionary for plants	obtain/make:	make functional flowchart
change cropdatabase to cropfactory	crops	make scientific basis – FAO 56/basic fertility reduction/YieldGap.org
make soil class	family	possibly expand scientific basis – AquaCrop/MMF
make interface for end-of-year	buttons	extract growth from above
add more crops	interface	obtain local prices
add labour
add SLM measures
add random events – drought/pest/cow herds
add tutorial

## Gant chart
				HOLIDAYS
#VALUE!	#VALUE!	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7	1	2	3	4	5	6	7
task	subtask	23/02/22	24/02/22	25/02/22	26/02/22	27/02/22	28/02/22	01/03/22	02/03/22	03/03/22	04/03/22	05/03/22	06/03/22	07/03/22	08/03/22	09/03/22	10/03/22	11/03/22	12/03/22	13/03/22	14/03/22	15/03/22	16/03/22	17/03/22	18/03/22	19/03/22	20/03/22	21/03/22	22/03/22	23/03/22	24/03/22	25/03/22	26/03/22	27/03/22	28/03/22	29/03/22	30/03/22	31/03/22	01/04/22	02/04/22	03/04/22	04/04/22	05/04/22	06/04/22	07/04/22	08/04/22	09/04/22	10/04/22	11/04/22	12/04/22	13/04/22	14/04/22	15/04/22	16/04/22	17/04/22	18/04/22	19/04/22	20/04/22	21/04/22	22/04/22	23/04/22	24/04/22	25/04/22	26/04/22	27/04/22	28/04/22	29/04/22	30/04/22	01/05/22	02/05/22	03/05/22	04/05/22	05/05/22	06/05/22	07/05/22	08/05/22	09/05/22	10/05/22	11/05/22	12/05/22	13/05/22	14/05/22	15/05/22	16/05/22	17/05/22	18/05/22	19/05/22	20/05/22	21/05/22	22/05/22	23/05/22	24/05/22	25/05/22	26/05/22	27/05/22	28/05/22	29/05/22	30/05/22	31/05/22	01/06/22	02/06/22	03/06/22	04/06/22	05/06/22	06/06/22	07/06/22	08/06/22	09/06/22	10/06/22	11/06/22	12/06/22	13/06/22	14/06/22	15/06/22	16/06/22	17/06/22	18/06/22	19/06/22	20/06/22	21/06/22	22/06/22	23/06/22	24/06/22	25/06/22	26/06/22	27/06/22	28/06/22	29/06/22	30/06/22	01/07/22	02/07/22	03/07/22	04/07/22	05/07/22	06/07/22	07/07/22	08/07/22	09/07/22	10/07/22	11/07/22	12/07/22	13/07/22	14/07/22	15/07/22	16/07/22
Develop AHF2.0
	refactor to use grid in stead of dictionary for plants
	change cropdatabase to cropfactory
	make soil class
	add fertility effect
	make interface for end-of-year
	add more crops
	add labour
	add SLM measures
	add random events – drought/pest/cow herds
	add tutorial
fill in local values/make game balanced
revise proposal
reach out to schools
develop curriculum around AHF									← Maybe this will need another week
Make questionnaire
conduct research on schools
process results
write thesis
	scientific background
	model/architeture explanation
	methods
	results